## 301 Redirect Map
301 Redirect Map — petittrain-morbihan.com → 3 new microsites
Set up these 301 (permanent) redirects at the old petittrain-morbihan.com domain level. This preserves SEO authority when new microsites go live. Replace `NEW_CARNAC_DOMAIN`, `NEW_QUIBERON_DOMAIN`, `NEW_VANNES_DOMAIN` with the actual production domains before implementing.
Old URL (from petittrain-morbihan.com) | Language | Redirect type | New URL (destination) | Notes / Priority
CARNAC — 6 URLs + PDFs
https://www.petittrain-morbihan.com/carnac-menhirs-petit-train/ | FR | 301 | https://NEW_CARNAC_DOMAIN/ | CRITICAL — highest-authority French slug (keyword-rich). Last modified 2025-08-07.
https://www.petittrain-morbihan.com/en/carnac/ | EN | 301 | https://NEW_CARNAC_DOMAIN/ | CRITICAL — TripAdvisor + OT Carnac backlinks point here.
https://www.petittrain-morbihan.com/de/carnac/ | DE | 301 | https://NEW_CARNAC_DOMAIN/ | French-only migration: point to homepage.
https://www.petittrain-morbihan.com/es/carnac/ | ES | 301 | https://NEW_CARNAC_DOMAIN/ | French-only migration: point to homepage.
https://www.petittrain-morbihan.com/it/carnac/ | IT | 301 | https://NEW_CARNAC_DOMAIN/ | French-only migration: point to homepage.
https://www.petittrain-morbihan.com/nl/carnac/ | NL | 301 | https://NEW_CARNAC_DOMAIN/ | French-only migration: point to homepage.
https://www.petittrain-morbihan.com/wp-content/uploads/...Brochure-Individuel-2024.pdf | — | 301 | https://NEW_CARNAC_DOMAIN/prices | Indexed PDF. Redirect to new prices page (or keep hosting the PDF with same filename for now).
https://www.petittrain-morbihan.com/wp-content/uploads/...Brochure-GROUPE-2024.pdf | — | 301 | https://NEW_CARNAC_DOMAIN/privatisation | Indexed PDF. Redirect to new group booking page.
QUIBERON — 6 URLs
https://www.petittrain-morbihan.com/quiberon-cote-sauvage-petit-train/ | FR | 301 | https://NEW_QUIBERON_DOMAIN/ | CRITICAL — highest-authority French slug. Last modified 2025-08-07.
https://www.petittrain-morbihan.com/en/quiberon/ | EN | 301 | https://NEW_QUIBERON_DOMAIN/ | Primary English landing.
https://www.petittrain-morbihan.com/de/quiberon/ | DE | 301 | https://NEW_QUIBERON_DOMAIN/ | French-only migration: point to homepage.
https://www.petittrain-morbihan.com/es/quiberon/ | ES | 301 | https://NEW_QUIBERON_DOMAIN/ | French-only migration: point to homepage.
https://www.petittrain-morbihan.com/it/quiberon/ | IT | 301 | https://NEW_QUIBERON_DOMAIN/ | French-only migration: point to homepage.
https://www.petittrain-morbihan.com/nl/quiberon/ | NL | 301 | https://NEW_QUIBERON_DOMAIN/ | French-only migration: point to homepage.
VANNES — 6 URLs
https://www.petittrain-morbihan.com/vannes-remparts-petit-train/ | FR | 301 | https://NEW_VANNES_DOMAIN/ | CRITICAL — highest-authority French slug. Last modified 2025-08-07.
https://www.petittrain-morbihan.com/en/vannes/ | EN | 301 | https://NEW_VANNES_DOMAIN/ | Primary English landing.
https://www.petittrain-morbihan.com/de/vannes/ | DE | 301 | https://NEW_VANNES_DOMAIN/ | French-only migration: point to homepage.
https://www.petittrain-morbihan.com/es/vannes/ | ES | 301 | https://NEW_VANNES_DOMAIN/ | French-only migration: point to homepage.
https://www.petittrain-morbihan.com/it/vannes/ | IT | 301 | https://NEW_VANNES_DOMAIN/ | French-only migration: point to homepage.
https://www.petittrain-morbihan.com/nl/vannes/ | NL | 301 | https://NEW_VANNES_DOMAIN/ | French-only migration: point to homepage.
NON-LOCATION (global pages on old domain)
https://www.petittrain-morbihan.com/ | FR | Keep OR 301 | https://NEW_CARNAC_DOMAIN/ (or keep as landing) | DECISION NEEDED: keep old domain as a landing page listing all 3 locations, OR redirect everything to Carnac? Recommend keeping as a choice page.
https://www.petittrain-morbihan.com/en/ | EN | Keep OR 301 | https://NEW_CARNAC_DOMAIN/ (or keep as landing) | Same decision as above.
https://www.petittrain-morbihan.com/de/ | DE | Keep OR 301 | Same | Same.
https://www.petittrain-morbihan.com/es/ | ES | Keep OR 301 | Same | Same.
https://www.petittrain-morbihan.com/it/ | IT | Keep OR 301 | Same | Same.
https://www.petittrain-morbihan.com/nl/ | NL | Keep OR 301 | Same | Same.
https://www.petittrain-morbihan.com/politique-de-confidentialite/ | FR | 301 | https://NEW_CARNAC_DOMAIN/politique-de-confidentialite (or similar on other sites) | Each new site has its own privacy page.
https://www.petittrain-morbihan.com/mentions-legales/ | FR | 301 | https://NEW_CARNAC_DOMAIN/mentions-legales | Each new site has its own legal page.
https://www.petittrain-morbihan.com/recrutement-petits-trains-morbihan/ | FR | 301 | https://NEW_CARNAC_DOMAIN/careers | All 3 new sites likely have a careers page.

## Backlinks To Update
Backlinks To Update — contact each source to change target URL to new domain
These third-party sites currently link to the OLD petittrain-morbihan.com URLs. After 301 redirects are live, contact each to update the link so authority transfers faster and user experience stays clean. Some you may not be able to edit directly — for those, 301 redirects alone will carry the signal, but a direct update is worth ~3x the weight.
Source | URL currently linking out | Current target (on old site) | New target (request update to) | Location | Contact / how to update
CARNAC backlinks
TripAdvisor — Le Petit Train Touristique de Carnac | https://www.tripadvisor.com/Attraction_Review-g187096-d7010664-Reviews-Le_Petit_Train_Touristique_de_Carnac-Carnac_Morbihan_Brittany.html | Old site homepage / EN carnac | https://NEW_CARNAC_DOMAIN/ | Carnac | Claim the listing (free) via TripAdvisor management center. Edit the 'Website' field.
OT Carnac (Office de Tourisme) | https://www.ot-carnac.fr/activites/petit-train-touristique-carnac-loief9f926d877e4/ | Old FR slug | https://NEW_CARNAC_DOMAIN/ | Carnac | Email the OT Carnac directly or call. Ask them to update the website URL on the listing.
Morbihan Tourism | https://morbihan.com/a-voir-a-faire/activites-et-loisirs/petit-train-touristique-carnac-carnac-fr-4408101/ | Old FR slug | https://NEW_CARNAC_DOMAIN/ | Carnac | Partner portal — likely requires email. Contact via morbihan.com contact form.
Brittany Tourism (EN) | https://www.brittanytourism.com/plan-my-holiday/things-to-do-see/all-activities/petit-train-touristique-carnac-carnac-en-2124087/ | Old EN URL | https://NEW_CARNAC_DOMAIN/ | Carnac | Contact Brittany Tourism via their B2B / partner portal.
Baie de Quiberon (UK) | https://www.baiedequiberon.co.uk/ | Old site link(s) | https://NEW_CARNAC_DOMAIN/ | Carnac | Contact via their website.
Bonjour.fun / Petit Futé / Camping Les Druides / Agence Contact (490 avis) | various | Old URLs | https://NEW_CARNAC_DOMAIN/ | Carnac | Individual outreach per domain.
Google Business Profile | — | Old URL likely set as website | https://NEW_CARNAC_DOMAIN/ | Carnac | Log into GBP, edit website field. Takes 1 minute. HIGHEST PRIORITY.
QUIBERON backlinks (likely analogs — verify)
TripAdvisor — Petit Train Quiberon | Search 'Petit Train Quiberon' on TripAdvisor to find exact listing URL | Old site | https://NEW_QUIBERON_DOMAIN/ | Quiberon | Claim listing, update website field.
OT Quiberon (Office de Tourisme) | https://www.quiberon.com/ | Old FR slug | https://NEW_QUIBERON_DOMAIN/ | Quiberon | Email/call the OT.
Morbihan Tourism (Quiberon listing) | Search site for 'petit train quiberon' | Old FR slug | https://NEW_QUIBERON_DOMAIN/ | Quiberon | Partner portal.
Brittany Tourism (Quiberon listing) | Search brittanytourism.com | Old EN URL | https://NEW_QUIBERON_DOMAIN/ | Quiberon | Partner portal.
Google Business Profile (Quiberon) | — | Old URL | https://NEW_QUIBERON_DOMAIN/ | Quiberon | Log into GBP, edit. HIGHEST PRIORITY.
VANNES backlinks (likely analogs — verify)
TripAdvisor — Petit Train Vannes | Search 'Petit Train Vannes' on TripAdvisor | Old site | https://NEW_VANNES_DOMAIN/ | Vannes | Claim listing, update website field.
OT Golfe du Morbihan Vannes | https://www.golfedumorbihan.bzh/ | Old FR slug | https://NEW_VANNES_DOMAIN/ | Vannes | Email/call the OT.
Morbihan Tourism (Vannes listing) | Search site for 'petit train vannes' | Old FR slug | https://NEW_VANNES_DOMAIN/ | Vannes | Partner portal.
Brittany Tourism (Vannes listing) | Search brittanytourism.com | Old EN URL | https://NEW_VANNES_DOMAIN/ | Vannes | Partner portal.
Google Business Profile (Vannes) | — | Old URL | https://NEW_VANNES_DOMAIN/ | Vannes | Log into GBP, edit. HIGHEST PRIORITY.

## Migration Checklist
Migration Checklist — order of operations
# | Task | Who / when
1 | Finish building all 3 new microsites (Carnac ✓, Quiberon TBD, Vannes TBD) | Dev — before domain switch
2 | Purchase/assign production domain for each of the 3 microsites | You — before DNS switch
3 | Deploy all 3 new sites to production on their final domains | Dev
4 | Set NEXT_PUBLIC_SITE_URL env var on each Vercel project to the final domain | Dev
5 | Add each new domain to Google Search Console; submit each /sitemap.xml | You
6 | Implement all 301 redirects from sheet 1 on petittrain-morbihan.com (via WordPress plugin like Redirection, or edit .htaccess directly) | Old-site host
7 | Verify redirects work: curl -I each old URL, check for 301 + correct Location header | Dev
8 | In Google Search Console for old petittrain-morbihan.com, use 'Change of address' tool for the Carnac paths → new Carnac domain (and repeat for Vannes/Quiberon if you split into 3 GSC properties) | You
9 | Update Google Business Profile: change website URL to new domain (all 3 locations) | You — DAY 1 priority
10 | Outreach to backlinks in sheet 2 — TripAdvisor first (highest DA), then OT listings, then tourism boards | You — first 30 days
11 | Monitor GSC 'Coverage' report for crawl errors for 30 days post-migration | You
12 | Monitor organic traffic in GA/GSC vs baseline — expect 10–30% temporary drop for 2–8 weeks as Google re-indexes; full recovery within 3 months IF redirects + backlinks are correctly done | You